|  |  | Project office: Ministry of Labour and Social Policy 14 Dame Gruev Str., 1000 Skopje |
| --- | --- | --- |

| Contract title: | Support to the Implementation of the Roma Strategy |
| --- | --- |
| Contract number: | 2010/258-484 |
| Subject: | FOURTH QUARTERLY REPORT - SUMMARY For the period 1 October – 31 December 2011 |

This Quarterly Report for the Project ‘Support to the Implementation of the Roma Strategy’ covers the project implementation activities in the period 1 October – 31 December 2011. It represents the major findings and results achieved from the work undertaken on the ground by the BBI Technical Assistance team. The format of the Report follows the structure of the previous one; and it includes the list of annexes and technical deliverables.

With regards to the use of human resources it reports on the deployment of a number of Non-key Experts in the areas of:

- Trainings on –

- (07-08 November 2011): EU institutions and their functioning, EU enlargement policy;

- (06-07 December 2011): Monitoring and Evaluation of LAPs;

- (19-20 December 2011): Web Communication;

- Conduct of the study tour in Brussels;

- Community Development – Project Component 2; LAP development workshops in Bitola, Berovo, and Sveti Nikole;

- Web design/Outline of information materials;

- Roma Decade - Logistical Support.

There were in total of 78,75 working days assigned to the (senior and junior) NKEs in the course of the reported period.

The use of incidental budget categories was dedicated to travel costs for implementing the study tour, and for the organisation of activity related workshop events:

- Study Tour to EU Institutions and other organisations in Brussels (14-18 November 2011);

- Training and workshop events were related to the above-mentioned topics.

The major achievements related to project Component 1 in the reporting period are:

- The implementation of the training plan which continued with the conduct of a series of three trainings on the above-mentioned topics. All of these trainings were delivered to the staff of the UISDR and the MwP Cabinet, and some of them included as participants also NCB members and local-level representatives.

- The study tour for the staff of the central level beneficiary institutions (MwP Cabinet and the UISDR at the MLSP, and one staff from the SEA) took place in Brussels from 14-18 November 2011. Its programme included a series of meetings with representatives of key EC institutions and EU-level organisations and networks. The study tour improved the cooperation between the project beneficiaries and provided a learning platform for them on the functioning of the EU institutions in relation to the enlargement process and the shaping and implementation of EU-level policies for Roma inclusion. The study tour focused on the identification of lessons learned from EU institutions, organisations, advocacy groups, etc., which are potentially transferable to the environment of the beneficiary country.

- Support to the implementation of the Roma Decade Presidency Programme – The implementation of this Programme continued and the TA team provided logistical and organizational support in this respect. The International Conference for Employment took place on 01-02 December 2011 in Skopje; and the project provided financial support from the incidental expenditures for ensuring simultaneous translation during the entire meeting and for part of the translation equipment.

- Implementation of the Communication Strategy and its Operational Plan continued with the formation and the work of the Coordinating Team for Communication (CTC), as recommended by the Communication Strategy. This team comprises 4 persons from the beneficiary institutions mandated with the mainly organisational tasks of collection and dissemination of concrete data on achievements under the Roma Strategy and the Decade for Roma Inclusion.

- The implementation of information activities continued, as also envisaged by the Communication Strategy. Different information materials – leaflets of the project and the RIC, project sticker, training certificate, project newsletter - were produced and are being disseminated at all trainings and public events on central and local level where the project is participating. The project’s webpage was launched and it is linked to the MLSP website.

Major activities related to project Component 2:

- The implementation of the training plan included trainings addressing local-level representatives, such as RIC staff, municipal officers for relations with minorities, and NGO representatives.

- RIC support – following the RIC assessment and a series of preparation activities, the actual support to the RIC capacity building is provided through the preparation of the RIC Manual of procedures, which was drafted during the reporting period. This process follows the recommendations of the concept note developed for the provision of support to the RICs, and it is linked with other project activities, such as LAP implementation support, capacity building interventions, communication activities and upgrading of the procedures of the UISDR and the MwP Cabinet.

- LAP revision / development – the actual process of revision of existing LAPs and development of new LAPs began during the reporting period. The focus is on three different groups of municipalities: 1) those with no LAPs at present; 2) those foreseeing a revision of LAPs; and 3) those which did not return the questionnaire sent during the assessment. For the purpose of increasing the interest and achieving the commitment on the part of the third group, the TA team sought and ensured the support of the Minister of Labour and Social Policy. The first three workshops for LAP development were conducted in Bitola, Berovo, and Sveti Nikole.

- Financial support to LAP implementation – project support for LAP priority measures started by approaching 13 target municipalities which had already developed LAPs: Shtip, Tetovo, Kumanovo, Delcevo, Bitola, Gostivar, Prilep, Suto Orizari, Kocani, Kriva Palanca, Probistip, Rankovce, and Vinica. These municipalities were informed by the project team about the possibility to jointly identify LAP measures to be supported by the project, so that they sent their ideas in two ‘waves’ – 28 November and 25 December 2011. Six municipalities expressed their interest by the first date, and 7 more ideas by the second one. At the end of the reporting period the project team together with the representatives of the CA and the project beneficiaries are in process of evaluation of the identified measures and in communication with the municipalities for improving them.

Further, the report also provides the plan of activities for the next 3-month period, which will be used as a management tool and also for monitoring purposes. The major focus in this period is placed on:

- Organisation of the next capacity building interventions (trainings), as indicated in the training plan;

- Upgrade of the work procedures of the UISDR and the MwP Cabinet employees, and the NCB; development of manuals of procedures, where relevant;

- Support to the MwP Cabinet in designing specific policies, improving co-operation with line Ministries, strengthening dialogue with civil society and the promotion of Roma Strategy priorities as part of national and sectoral policies;

- Support to the organisation of the next Decade Presidency events;

- Further dissemination of information materials and production of additional Communication Strategy related deliverables – next issues of the project newsletter, improvement of the project webpage, etc.;

- Further implementation of the Communication Strategy and continuation of the CTC work;

- Start of joint implementation of the LAP-related measures;

- Further actions to support RIC functions – training, finalization and introduction of the RIC Manual.

Annexes are included at the end of the report.

|  | Support to the implementation of the Roma Strategy This project is funded by the European Union |  |
| --- | --- | --- |